## MediTouch Gantt
MONTLY TASK GANTT CHART
PROJECT NAME |  | START DATE | END DATE
MEDITOUCH |  | 2026-01-01 | 2026-03-31
[7 empty] | PHASE ONE | [5 empty] | PHASE TWO
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (weeks) | % COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12
Phase One: Core App Development
1 | Project conception and initiation | Krrish,udayraj | 2026-01-01 | 2026-01-08 | 1 | 100% | bar: PHASE ONE WEEK 1
1.2 | Theme and UI setup | Udayraj,shravani | 2026-01-08 | 2026-01-22 | 2 | 100% | bar: PHASE ONE WEEK 2 to PHASE ONE WEEK 3
1.3 | Firebase initialization and auth flow | Shravani,anushka | 2026-01-15 | 2026-01-29 | 2 | 100% | bar: PHASE ONE WEEK 3 to PHASE ONE WEEK 4
1.4 | Firestore/repository setup | Anushka,udayraj | 2026-01-22 | 2026-02-05 | 2 | 100% | bar: PHASE ONE WEEK 4 to PHASE ONE WEEK 5
1.5 | Patient home screen | Krrish,udayraj | 2026-01-29 | 2026-02-12 | 2 | 100% | bar: PHASE ONE WEEK 5 to PHASE ONE WEEK 6
1.6 | Medicines/reminders screen | Udayraj | 2026-02-05 | 2026-02-19 | 2 | 100% | bar: PHASE ONE WEEK 6 to PHASE TWO WEEK 7
1.7 | Appointment booking and management | Shravani,anushka | 2026-02-12 | 2026-02-26 | 2 | 100% | bar: PHASE TWO WEEK 7 to PHASE TWO WEEK 8
1.8 | Profile screen and BMI logic | Anushka | 2026-02-26 | 2026-03-05 | 1 | 100% | bar: PHASE TWO WEEK 9
Phase Two: Doctor/Admin and Release
2.1 | Admin dashboard | Krrish,udayraj | 2026-02-12 | 2026-02-26 | 2 | 100% | bar: PHASE TWO WEEK 7 to PHASE TWO WEEK 8
2.2 | Appointment review and status actions | Udayraj,shravani | 2026-02-19 | 2026-03-05 | 2 | 100% | bar: PHASE TWO WEEK 8 to PHASE TWO WEEK 9
2.3 | Patient list and profile viewing | Shravani,anushka | 2026-02-26 | 2026-03-12 | 2 | 100% | bar: PHASE TWO WEEK 9 to PHASE TWO WEEK 10
2.4 | Chat and messaging | Anushka,udayraj | 2026-02-26 | 2026-03-12 | 2 | 100% | bar: PHASE TWO WEEK 9 to PHASE TWO WEEK 10
2.5 | Prescription management | Krrish,udayraj | 2026-03-05 | 2026-03-19 | 2 | 100% | bar: PHASE TWO WEEK 10 to PHASE TWO WEEK 11
2.6 | Symptom checker | Udayraj | 2026-03-05 | 2026-03-19 | 2 | 100% | bar: PHASE TWO WEEK 10 to PHASE TWO WEEK 11
2.7 | Testing, polishing, and final release | Shravani,anushka | 2026-03-12 | 2026-03-26 | 2 | 100% | bar: PHASE TWO WEEK 11 to PHASE TWO WEEK 12